## Sheet1
Machine Learning for Professional Chess Match Outcome Prediction
Objective | Task | Deliverables | Start Date | End Date | No of Weeks | No of Days
1.1 | Determine programming language and available libraries. | Decision on programming language and selected libraries that will be used to create both a dataset and a machine learning model. | 2023-11-06 | 2023-11-12 | 1 | 7
2.1 | Find Application Programming Interface (API) for data collection. | Located an API or application that allows for the extraction of data from online chess platforms. | 2023-11-13 | 2023-11-26 | 2 | 14
2.2 | Investigate the available API calls to gain an understanding of what can be collected for the dataset. | Understanding of what data should and can be collected through the previously found API. | 2023-11-27 | 2023-12-10 | 2 | 14
3.1 | Begin using the API to collect any data that is deemed relevant for the dataset used for training the machine learning model. | Semi-structured data acquired usingpreviously found API. | 2023-12-11 | 2023-12-31 | 3 | 21
3.2 | Turn semi-structured historical chess data into structured data. | Historical chess data in structured format ready cleaning and preprocessing | 2024-01-01 | 2024-01-14 | 2 | 14
4.1 | Carry out data cleaning to remove any inaccurate or unwanted data within the dataset. | Cleaned dataset with no errors ready for use in the creation of the feature set | 2024-01-15 | 2024-01-28 | 2 | 14
4.2 | Carry out data preprocessing, identifying and features that can be made or used from structured historical chess dataset. | Feature set ready for machine learning use. | 2024-01-29 | 2024-02-18 | 3 | 21
5.1 | Determine two different supervised machine learning algorithms that can be used in reference to the feature set and output requirements. | Two Machine learning algorithms selected for use. | 2024-02-19 | 2024-02-25 | 1 | 7
5.2 | Train one of the machine learning algorithms on the feature set. | One machine learning model trained on the created feature set. | 2024-02-26 | 2024-03-10 | 2 | 14
5.3 | Train second machine learning algorithm on the feature set. | Both machine learning models training on the created feature set. | 2024-03-11 | 2024-03-24 | 2 | 14
6.1 | Evaluate Both of the machine learning models using relevant metrics. | Obtain valuable metrics that can be used to evaluate both machine learning models performance. | 2024-03-25 | 2024-04-07 | 2 | 14
6.2 | Use collected metrics about both machine learning models to compare the difference in performance. | Identified which model performed better on the chess feature set. | 2024-04-08 | 2024-04-14 | 1 | 7
6.3 | Compare the results of machine learning models against other relevant machine learning models in the realm of sport match outcome prediction | Identified how well the created model performs with reference to other models within the same research area. | 2024-04-15 | 2024-04-28 | 2 | 14